## Open POA&M Items
FedRAMP POA&M Template
System Name: Tutorial System
Date Generated: 2026-06-17
Instructions: Enter one weakness per row starting at row 6
POAM ID | Weakness Name | Weakness Description | Controls | Office/Role | Weakness Detector Source | Status | Original Detection Date | Scheduled Completion Date | Revised Completion Date | Actual Completion Date | Planned Milestones | Milestone Changes/Log | Original Risk Rating | Asset Identifier
2026-0001 | Outdated Linux Kernel Vulnerability (CVE-2024-1086) | Use-after-free vulnerability in the Linux kernel Netfilter subsystem allows local privilege escalation to root. | SI-2 | Infrastructure Engineering Team | Tenable Nessus Scan v8.15 | Ongoing | 2026-01-15 | 2026-02-15 | 2026-03-15 |  | (1) 2026-01-20: Identify all affected EC2 instances. (2) 2026-02-01: Stage patched AMIs in staging environment. (3) 2026-02-14: Deploy patches to production via CI/CD. | Extension requested on 2026-02-10: Staging environment testing revealed a breaking dependency change with our core container runtime application. Delayed production deployment by 30 days to resolve. | High | prod-app-srv-01, prod-app-srv-02, prod-api-srv-05
2026-0002 | Cross-Site Scripting (XSS) in Search Endpoint | Improper input sanitization on the public query input allows malicious actors to inject arbitrary scripts via refraction. | SI-10 | Application Security Team | Veracode SAST Pipeline | Completed | 2026-02-01 | 2026-03-01 |  | 2026-02-24 | (1) 2026-02-05: Refactor endpoint code to implement context-aware output encoding. (2) 2026-02-18: Pass regression testing suite. | None. Remediation completed ahead of schedule. | Moderate | web-frontend-cluster (ASG-01)
2026-0003 | Unencrypted AWS S3 Storage Buckets | Two object storage buckets inside the production boundaries lack default server-side encryption (SSE-KMS) configurations. | SC-28 | Cloud DevOps Team | Prisma Cloud CSPM Scan | Ongoing | 2026-02-10 | 2026-05-10 |  |  | (1) 2026-03-01: Update Terraform state definitions to mandate AWS KMS keys. (2) 2026-04-01: Remediate existing historical data blocks. | None. Progress tracking actively within the standard 90-day window allowed for Moderate findings. | Moderate | s3://fedramp-compliance-logs, s3://fedramp-user-uploads
2026-0004 | Incomplete Physical Security Logging at Alternate Site | The secondary disaster recovery data center facility fails to archive digital badge visitor entry logs for the required 1-year period. | PE-3 | Compliance and Facility Ops | 3PAO Annual Security Assessment Report (SAR) | Ongoing | 2026-03-01 | 2026-09-01 |  |  | (1) 2026-04-15: Update SLA with colocation facility vendor. (2) 2026-06-01: Configure automated backup exports to system boundary. | None. | Low | DR-DataCenter-Facility-Equinix-DC2
2026-0005 | Database Inactive Session Timeout Exceeded | Production PostgreSQL database nodes allow interactive sessions to remain idle indefinitely without terminating connection context. | AC-12 | Database Administration (DBA) | Aqua Security Container Scan | Ongoing | 2026-03-15 | 2026-06-15 |  |  | (1) 2026-04-01: Update pg_hba.conf parameters. (2) 2026-04-15: Set dynamic idle_in_transaction_session_timeout variables. | None. | Moderate | db-cluster-primary, db-cluster-replica-01
2026-0006 | Critical Remote Code Execution in Component (Log4j-like) | An open-source logging library dependency allows an unauthenticated attacker to execute code remotely via JNDI injection. | SI-2 | DevSecOps / Release Engineering | Snyk Software Bill of Materials (SBOM) Scan | Completed | 2026-04-01 | 2026-04-02 |  | 2026-04-02 | (1) 2026-04-01: Evacuate vulnerable container versions. (2) 2026-04-02: Force global dependency bump across all repository branches. | None. Remediation forced immediately due to strict emergency patch guidelines for zero-day vulnerabilities. | High | All K8s Microservice Pods (Namespace: Production)